## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Shaikh Mohammad Affan Inayat | 2025-09-26 | Azure Speech SDK throwing authentication error on first run | Sprint 1 | Shaikh Mohammad Affan Inayat | Logical | Added explicit key validation + clear error message | 2025-09-26 | Closed | Fixed before Hindi testing
2 | Nallagonda Surya Vamsi | 2025-09-28 | Translation returning empty string when input text is too long (>500 chars) | Sprint 1 | Nallagonda Surya Vamsi | Logical | Chunkplit long text into chunks of 400 chars with overlap | 2025-09-28 | Closed | Handles long commentary now
3 | Ravalika Tulagapu | 2025-10-04 | Pipeline crashing when no audio input received for >30s | Sprint 2 | Ravalika Tulagapu | Logical | Added timeout handler + graceful session close | 2025-10-04 | Closed | Prevents server crash
4 | Chikkam Bala Satya Aditya | 2025-10-06 | FastAPI not returning proper CORS headers in local dev | Sprint 2 | Chikkam Bala Satya Aditya | Standards | Added CORSMiddleware with allow_all origins in dev mode | 2025-10-06 | Closed | Frontend integration smooth
5 | Sanket S Mathpati | 2025-10-10 | WebSocket disconnecting randomly during live streaming | Sprint 3 | Sanket S Mathpati | Logical | Implemented ping/pong every 15s + auto-reconnect logic | 2025-10-10 | Closed | Stable 10+ min streams
6 | Rishika Roy | 2025-10-13 | Hindi TTS producing robotic voice for certain prosody | Sprint 3 | Rishika Roy | User Interface | Added SSML prosody tags + voice fallback to en-IN-PrabhatNeural | 2025-10-13 | Closed | Natural sounding output
7 | Sadhvika Bhaskar | 2025-10-17 | WER calculation failing when no reference transcript provided | Sprint 4 | Sadhvika Bhaskar | Logical | Added guard clause + default WER = 100% when reference missing | 2025-10-17 | Closed | Metrics now always available
8 | Rajeev Reddy | 2025-10-20 | Memory leak in continuous recognition mode | Sprint 4 | Rajeev Reddy | Maintainability | Properly disposed SpeechRecognizer object after each session | 2025-10-20 | Closed | Memory usage stable
9 | Sanket S Mathpati | 2025-10-24 | Redis queue filling up during high load (no worker consuming) | Sprint 5 | Sanket S Mathpati | Logical | Started background Celery worker + added health check | 2025-10-24 | Closed | Queue clears instantly
10 | Nandhana C H | 2025-10-28 | Rate limiter not resetting after 1 minute | Sprint 5 | Nandhana C H | Logical | Fixed Redis key expiry from 60s → 61s to avoid race condition | 2025-10-28 | Closed | Rate limiting now accurate
11 | Sadhvika Bhaskar | 2025-11-01 | Inconsistent logging format across modules | Sprint 6 | Sadhvika Bhaskar | Standards | Centralized logging config with structlog + JSON format | 2025-11-01 | Closed | Production-ready logs
12 | Jayahar J | 2025-11-03 | Missing type hints in services/speech_recognizer.py | Sprint 6 | Jayahar J | Maintainability | Added complete type annotations + ran mypy | 2025-11-03 | Closed | 100% typed code
13 | Thariga Shrinithi R | 2025-11-07 | README instructions failing on Windows (path separator issue) | Sprint 7 | Thariga Shrinithi R | Standards | Used pathlib + cross-platform example commands | 2025-11-07 | Closed | Works on Windows/Linux/macOS
14 | Nallapaneni Lakshmi Sowjanya | 2025-11-09 | Demo video showing old latency numbers | Sprint 7 | Nallapaneni Lakshmi Sowjanya | Standards | Re-recorded demo with updated overlay showing real-time latency | 2025-11-09 | Closed | Final demo accurate
15 | Srikakulapu Sravanthi | 2025-11-11 | Missing .gitignore for venv and pycache | Sprint 7 | Srikakulapu Sravanthi | Logical | Added comprehensive .gitignore (Python + VSCode + env) | 2025-11-11 | Closed | Repo stays clean
16 | Pooja Kempalingannavar | 2025-11-13 | API returning 200 instead of 422 on invalid JSON payload | Sprint 7 | Pooja Kempalingannavar | Logical | Added Pydantic validation exception handler → returns 422 | 2025-11-13 | Closed | Proper REST behavior
17 | Akshit Sharma | 2025-11-14 | Final presentation slide had wrong WER number (old value) | Sprbnt 7 | Akshit Sharma | Maintainability | Updated slide deck with latest metrics: WER EN=8.2%, HI=12.4%, Latency=1.42s | 2025-11-14 | Closed | Presentation 100% accurate

## Sheet2
Logical
User Interface
Maintainability
Standards
Others